KHULA GYAN

Cited answers from official Nepali documents

Project Blueprint: idea, flow, model structure and 16-day execution plan

| Item | Detail |
| --- | --- |
| Event | Frogtoberfest 2026 (open-source project, built in about two weeks) |
| Project type | Open-source Retrieval-Augmented Generation (RAG) assistant for Nepali government services |
| Team | 4 members: Member 1 (Data), Member 2 (Retrieval), Member 3 (Generation & Evaluation), Leader (Integration, API, UI, Repo) |
| Working window | Day 0 = Oct 8-9, 2026. Days 1-16 = Oct 10 to Oct 25, 2026. Code freeze: Oct 23. Submission target: Oct 25. |
| Repository | github.com/HAliveKP/khula-gyan (adjust if the repo name differs) |
| Document version | v1.1, updated Oct 8, 2026 (Streamlit UI calling the pipeline directly, deployed on Hugging Face Spaces). Re-confirm the official Frogtoberfest deadline and submission rules (Day 3). |

This document is written so that a person or any AI assistant can read it from start to finish and understand what is being built, why, how it fits together, and what each team member does on each day.

# 0. How to use this document

## Document map

| Section | What it answers |
| --- | --- |
| 1. Project at a glance | What is being built, in one page |
| 2. The problem | Who is affected, what goes wrong, what it costs |
| 3. The idea | How the product closes the gap |
| 4. How AI powers it | The exact jobs AI does and what comes out |
| 5. Goals, scope and non-goals | What is in and what is deliberately out |
| 6. End result and success metrics | What "done" looks like, with numbers |
| 7. Project flow | How a question travels through the system, and how the build flows |
| 8. Repository structure | Folders and who owns them |
| 9. Data design and interfaces | The contracts that let four people work in parallel |
| 10. Model structure | Every model and tool, why it was chosen, fallbacks, prompt, guard logic, how to start |
| 11. Evaluation plan | How quality is measured and improved |
| 12. Team roles and handoff to the leader | Who owns what; how code reaches the leader |
| 13. 16-day execution plan | Phase overview, then the daily task table for all 4 members |
| 14. Risks and fallbacks | What can go wrong and what to do |
| 15. Definition of done and glossary | Final checklist and plain-language terms |
| Appendix A | Copy-paste starter prompt for any AI assistant |

CONTEXT FOR AI ASSISTANTS (read this first) Project: Khula Gyan is an open-source assistant that answers questions about Nepali government procedures (driving license, citizenship certificate, passport) in Nepali and English, using ONLY a library of official documents. Every answer carries citations (document + page). If the documents do not support an answer, the system says "not found in official sources" instead of guessing. Technique: Retrieval-Augmented Generation (RAG) with hybrid search (dense + BM25), a cross-encoder reranker, an evidence guard, and an evaluation harness that tracks accuracy and hallucination rate. Team: 4 students, 16 days (Oct 10-25, 2026). Roles: Member 1 Data, Member 2 Retrieval, Member 3 Generation & Evaluation, Leader Integration/API/UI/Repo. Rules for the AI: (1) Follow the interface contracts in section 9 exactly. (2) Never answer civic or legal questions from model memory; answers must come from retrieved passages. (3) Ask which member and which day the user is working on, then do that day's tasks from section 13. (4) Produce code that runs, in small files, matching the repo structure in section 8. (5) Keep the language simple; the team are second-year university students.

# 1. Project at a glance

Name: Khula Gyan ("open knowledge"). Tagline: Cited answers from official Nepali documents.

One-sentence summary: A user asks a question in Nepali or English ("What documents do I need to renew my driving license?"); the system finds the exact passages in official documents, writes a plain-language answer with a checklist, shows the document and page it came from, and refuses to answer when the documents do not contain the answer.

| Question | Short answer |
| --- | --- |
| Who is it for? | Ordinary citizens in Nepal dealing with government procedures; also developers who want an open dataset and pipeline |
| What does it do? | Answers procedure questions with citations, checklists (documents, fees, steps) and an honest "not found" when evidence is missing |
| What makes it different? | Evidence-first: every claim is traceable to a page; an evaluation suite measures hallucination; the library and test set are open for contributors |
| Core AI technique | RAG: embeddings + hybrid retrieval + reranker + guarded LLM generation |
| What will be delivered? | Working web app deployed on Hugging Face Spaces, optional REST API, open document library, evaluation set (100 questions) with a results table, documentation, demo video |
| Scope (v1.0) | 3 services: driving license, citizenship certificate, passport (4th service is a stretch goal) |
| Time | 16 working days, Oct 10-25, 2026 |

# 2. The problem

Who is affected. Citizens in Nepal who need to follow government procedures such as renewing a license, applying for a citizenship certificate, or applying for a passport. First-time applicants, people from rural areas, and people with limited digital experience are hit hardest.

What goes wrong. Official information is scattered across PDFs, notices and websites. Many files are scanned images, and the language is formal legal Nepali. People cannot easily tell which document is current or what exactly is required, so they depend on middlemen and word of mouth. Existing chatbots are English-first and often invent answers, which is dangerous when the topic is law, money or identity.

What it costs if it stays unsolved. Wrong or missing paperwork, repeated office visits, lost days of wages, fees paid to agents who "know the process", and in the worst case rejected applications or missed deadlines. Misleading answers from tools that hallucinate make the situation worse because people trust them.

# 3. The idea

Khula Gyan is an open-source assistant that answers procedure questions in Nepali and English using only a curated, open library of official documents.

- Cited answers: every answer lists the exact document and page, with a short quote, so the user can verify it.

- Checklist output: documents required, fees, steps, and where to go, in simple language.

- Honest refusal: if the sources do not support an answer, the system says so rather than guessing.

- Open by design: the document library, scripts and test set are open; contributors add a new service by adding documents and test questions, without touching the core code.

- Measured quality: an evaluation suite reports retrieval accuracy, citation accuracy and hallucination rate for every version, so improvements are visible and honest.

# 4. How AI powers it

AI does five separate jobs inside the product:

| Job | What the AI does | What comes out |
| --- | --- | --- |
| Extracting | OCR reads scanned pages; text is cleaned and split into chunks; an embedding model turns each chunk into a vector (meaning-based fingerprint) | A searchable index of passages, each tagged with document and page |
| Retrieving | Dense (meaning) search and keyword (BM25) search find candidates; a cross-encoder reranker re-scores them | The 5 most relevant passages with scores |
| Judging | A guard decides if the evidence is strong enough, using a score threshold and a second LLM check "is every claim supported?" | A decision: answer, or "not found in official sources" |
| Generating | A language model writes a plain-language answer and checklist using only the supported passages, in the language of the question | Structured JSON: answer, checklist, citations, confidence |
| Evaluating | An evaluation harness (with an LLM judge plus human spot-checks) scores every version on a fixed question set | A results table: hit@5, citation accuracy, correctness, hallucination, refusal accuracy |

# 5. Goals, scope and non-goals

### Goals

- Working end-to-end product by Day 3 (even if rough), then improve it with measured experiments.

- Support Nepali, English and mixed-language questions for 3 services.

- Show a results table with baseline vs final numbers, proving each improvement.

- Be genuinely open-source ready: licence, contribution guide, issue templates, "good first issue" tickets, a guide to add a new service.

### Non-goals (do not build these in 16 days)

- Legal advice or case-specific advice. The tool explains official procedures only and says so in a disclaimer.

- Covering all government services. Depth and accuracy on 3 services beat shallow coverage of 20.

- Training a large model from scratch. We use pretrained models and focus on the pipeline and evaluation.

- User accounts, payments, or mobile apps.

# 6. End result and success metrics

### Deliverables on Oct 25

| # | Deliverable | Done when |
| --- | --- | --- |
| 1 | Streamlit web app deployed on Hugging Face Spaces (+ optional REST API in the repo) | Anyone can open the link, ask a question, and see a cited answer in Nepali or English |
| 2 | Document library for 3 services | At least 10 official documents, each listed with URL and usage status in docs/data-sources.md |
| 3 | Retrieval + generation pipeline | Hybrid search, reranker, guard and structured output working with one command to run |
| 4 | Evaluation set and results | 100 questions; results table with baseline vs final; error analysis written up |
| 5 | Open-source package | LICENSE, CONTRIBUTING, issue templates, 8+ good-first-issue tickets, add-a-service guide |
| 6 | Documentation | README (problem, demo, architecture, results, how to run), architecture.md |
| 7 | Demo video + submission text | 2-3 minute video; Problem / Idea / How AI powers it answers ready to paste |

### Quality targets (aim for these; report the real numbers even if lower)

| Metric | Meaning | Baseline (Day 3) | Target (Day 14) |
| --- | --- | --- | --- |
| Retrieval hit@5 | The right page is among the top 5 retrieved passages | record | 85% or higher |
| Citation accuracy | The cited document and page really contain the answer | record | 90% or higher |
| Answer correctness | The answer matches the expected facts (LLM judge + human spot-check) | record | 75% or higher |
| Hallucination rate | Answers containing claims not supported by the passages | record | 5% or lower |
| Correct refusal | Out-of-scope or unsupported questions are refused | record | 90% or higher |
| False refusal | Answerable questions wrongly refused | record | 15% or lower |
| Latency (p95) | Time to answer, 95 percent of requests | record | 8 seconds or less |

# 7. Project flow

## 7.1 What the user experiences

- The user opens the web app and types a question in Nepali, English or a mix.

- The system shows a short answer plus a checklist (documents, fees, steps, where to go).

- Below it, citation cards show the document name, page number and the supporting quote.

- If the evidence is weak, the system shows "not found in official sources" and suggests visiting the official office or website.

- The user can give thumbs up / down feedback, which is saved for later improvement.

## 7.2 What happens inside, step by step

USER QUESTION

|

v

[1] Query processing   - detect language, expand with Nepali/English glossary, optional service filter

|

v

[2] Hybrid retrieval   - dense vector search (bge-m3) + BM25 keyword search -> fuse with RRF -> top 20

|

v

[3] Reranker           - cross-encoder re-scores top 20 -> keep top 5 with scores

|

v

[4] Evidence guard     - best score above threshold?  NO -> return "not found"

|  YES

v

[5] LLM generation     - answer ONLY from the 5 passages; output JSON with citations

|

v

[6] Support check      - second LLM call: is every claim supported?  NO -> return "not found"

|  YES

v

[7] Response           - answer + checklist + citations + confidence + disclaimer

How the UI connects (deployment-friendly): the Streamlit app imports one function, ask(query) from src/pipeline.py, which runs steps 1 to 7 and returns the AskResponse. The UI therefore calls the pipeline directly and only one app needs to be deployed. The FastAPI app in src/api/ is a thin optional wrapper around the same ask() for contributors who want an HTTP API; it is not deployed.

## 7.3 Offline flow: how the library is built

data/raw/ (official PDFs, pages)

-> text extraction (PyMuPDF / pdfplumber; Tesseract OCR for scans)

-> cleaning (Unicode NFC, remove headers/footers, fix Devanagari)

-> chunking (300-500 tokens, 50 overlap, keep source + page)

-> embedding (bge-m3) -> ChromaDB index   +   BM25 index

-> data/processed/*.jsonl  (one chunk per line)

## 7.4 How the build itself flows

Build a thin end-to-end version first (Days 1-3), measure a baseline, then improve one thing at a time, running the evaluation after every change. Every improvement goes through a pull request to the dev branch, which the leader reviews and merges. A result that does not improve the numbers is dropped, not kept.

# 8. Repository structure

khula-gyan/

|-- data/

|   |-- raw/                 # downloaded originals (not committed if licence unclear)

|   `-- processed/           # cleaned text + chunks (JSONL)            [Member 1]

|-- src/

|   |-- ingest/              # extract, clean, chunk, embed, index      [Member 1 + 2]

|   |-- retrieval/           # search, BM25, fusion, reranker           [Member 2]

|   |-- generation/          # prompt, answer, guard, validation        [Member 3]

|   |-- pipeline.py          # ask(query) = search + answer, used by the UI [Leader]

|   `-- api/                 # optional FastAPI wrapper (not deployed)  [Leader]

|-- frontend/                # Streamlit UI (app.py calls ask() directly) [Leader]

|-- eval/

|   |-- questions.jsonl      # 100 test questions                       [Member 1 + 3]

|   `-- run_eval.py          # metrics script                           [Member 3]

|-- scripts/                 # download_data.py, make targets

|-- docs/                    # data-sources, results, architecture, error-analysis, add-a-service

|-- config.yaml              # all model names and thresholds in one place

|-- .env.example             # API key placeholders (never commit real keys)

|-- .github/ISSUE_TEMPLATE/

|-- README.md  CONTRIBUTING.md  CODE_OF_CONDUCT.md  LICENSE  requirements.txt

# 9. Data design and interfaces

These contracts are fixed on Day 0. Each member codes against them, so nobody waits for anybody else. If a contract must change, the leader approves it and announces it to the whole team.

### 9.1 Chunk (one line of data/processed/*.jsonl)

{"id": "dl_renewal_p2_c1",

"text": "To renew a driving license you must submit ...",

"source": "dotm_license_renewal.pdf",

"page": 2,

"service": "driving_license",     // driving_license | citizenship | passport

"lang": "ne"}                      // ne | en

### 9.2 Retrieval function (Member 2)

# src/retrieval/search.py

def search(query: str, k: int = 5, service: str | None = None) -> list[dict]:

"""Return top-k chunks: {id, text, source, page, service, lang, score}"""

### 9.3 Generation function (Member 3)

# src/generation/answer.py

def answer(query: str, chunks: list[dict]) -> dict:

"""Return an AskResponse (9.4). Must refuse if evidence is weak."""

### 9.3b Pipeline function (Leader)

# src/pipeline.py

def ask(query: str, service: str | None = None) -> dict:

"""search() -> rerank -> guard -> answer(). Returns an AskResponse (9.4)."""

# The Streamlit UI calls ask() directly. The optional POST /ask endpoint just wraps it.

### 9.4 AskResponse (returned by answer() and ask(); also by the optional POST /ask)

{

"status": "answered",              // "answered" | "not_found"

"language": "ne",                  // language of the answer

"answer": "...",

"checklist": {"documents": [], "fees": [], "steps": [], "where": ""},

"citations": [{"source": "file.pdf", "page": 2, "quote": "..."}],

"confidence": "high",              // high | medium | low

"disclaimer": "Verify with the official office before submitting."

}

### 9.5 Evaluation question (one line of eval/questions.jsonl)

{"id": "q001", "q": "License renew garna k k kagaj chahincha?", "lang": "mixed",

"service": "driving_license", "type": "answerable",   // answerable | out_of_scope

"expected": ["citizenship copy", "medical certificate"],

"must_cite": {"source": "dotm_license_renewal.pdf", "page": 2}}

Question mix for the final 100: about 80 answerable and 20 out-of-scope; about 40 Nepali, 40 English, 20 mixed or Romanized Nepali; spread evenly over the services.

# 10. Model structure

Models and tools are chosen to be free or low-cost, multilingual, and replaceable. All names live in config.yaml so a model can be swapped without changing code. Verify the Nepali quality of each choice on your own eval questions; do not assume.

| # | Stage | Recommended | Fallback | Output |
| --- | --- | --- | --- | --- |
| 1 | Text extraction | PyMuPDF or pdfplumber for digital PDFs; Tesseract (nep+eng) for scans | Use text-based sources only; skip bad scans | Raw text per page |
| 2 | Cleaning | Python unicodedata (NFC), regex rules | n/a | Clean text |
| 3 | Chunking | Paragraph / heading aware splitter, 300-500 tokens, 50 overlap | Fixed-size splitter | Chunk JSON (9.1) |
| 4 | Embedding | BAAI/bge-m3 (multilingual) | intfloat/multilingual-e5-base | One vector per chunk |
| 5 | Vector store | ChromaDB (persistent, metadata filters) | FAISS | Dense search results |
| 6 | Keyword search | rank_bm25 | n/a | Keyword ranked list |
| 7 | Fusion | Reciprocal Rank Fusion (k = 60) | Dense only | Merged top 20 |
| 8 | Reranker | BAAI/bge-reranker-v2-m3 (cross-encoder) | Skip; keep fusion order | Top 5 with scores |
| 9 | Evidence guard | Score threshold + LLM support check | Threshold only | answer / not_found |
| 10 | Generation | An instruction-following LLM via API (choose one with a free or student tier; name set in .env) | Open-weights model such as Qwen2.5-7B-Instruct | AskResponse JSON |
| 11 | Evaluation | run_eval.py + LLM-as-judge + human spot-check of 20 answers | Human only | Results table |

### 10.1 config.yaml (single source of truth)

embedding_model: BAAI/bge-m3

reranker_model: BAAI/bge-reranker-v2-m3

llm_model: ${LLM_MODEL}          # read from .env

chunk_tokens: 400

chunk_overlap: 50

retrieve_k: 20                   # candidates before reranking

final_k: 5                       # passages given to the LLM

rrf_k: 60

guard_min_score: 0.35            # calibrate on Day 5

max_latency_seconds: 8

### 10.2 Prompt template (Member 3 refines it on Days 4 and 12)

SYSTEM:

You are Khula Gyan, an assistant that explains Nepali government procedures.

Use ONLY the numbered passages below. Do not use outside knowledge.

If the passages do not contain the answer, return status "not_found".

Answer in the same language as the question (Nepali, English, or both if mixed).

Every statement must be supported by at least one citation (source + page + short quote).

Give a checklist: documents, fees, steps, where to go. Leave a field empty if unknown.

Return valid JSON matching the AskResponse schema. Do not add any text outside the JSON.

PASSAGES:

[1] (dotm_license_renewal.pdf, p.2) ...

[2] ...

QUESTION: {question}

### 10.3 Guard logic

passages = rerank(fuse(dense(q), bm25(q)))[:5]

if passages[0].score < guard_min_score:            return NOT_FOUND

draft = llm(prompt(q, passages))

if not valid_json(draft):  draft = llm(retry)       # one retry only

if not llm_check_supported(draft, passages):        return NOT_FOUND

if any(c not in passages for c in draft.citations): return NOT_FOUND

return draft

### 10.4 Getting started (every member, Day 0)

git clone https://github.com/HAliveKP/khula-gyan.git && cd khula-gyan

python -m venv .venv

source .venv/bin/activate            # Windows: .venv\Scripts\activate

pip install sentence-transformers chromadb rank_bm25 pymupdf pdfplumber \

fastapi uvicorn streamlit pyyaml python-dotenv pytesseract

# Tesseract with Nepali: install Tesseract, then add the "nep" language data file

cp .env.example .env                 # add LLM_MODEL and API key (never commit .env)

git checkout -b feature/<yourname>-<task>

### 10.5 Deployment: Streamlit on Hugging Face Spaces

- Why this host: the embedding model and reranker need several GB of memory. Hugging Face Spaces free CPU hardware has far more RAM than Streamlit Community Cloud, so the app is less likely to crash on startup. Check the current limits when you deploy.

- Setup: create a free Space with the Streamlit SDK and connect it to the repo (follow the current Hugging Face Spaces guide for the exact config: a header block in the Space README names the SDK and the app file, which is frontend/app.py).

- Secrets: put the LLM API key in the Space secrets settings and read it from environment variables. Never commit it.

- Index: build the index on first start if it is missing, or commit a small prebuilt index (check its size). Load models once with st.cache_resource so each question does not reload them.

- Speed: free CPU is slow. Measure latency on the first test deploy (Day 5). If it is too slow, use multilingual-e5-base or drop the reranker and compare eval numbers.

- Demo day: free Spaces sleep when idle, so open the app a few minutes before the demo. Keep the recorded demo video as a backup.

- Fallback hosts: Render, or any cloud VM with Docker, if the Space cannot handle the models.

Why this structure is "perfect" for a 16-day build Each stage has one owner, one input and one output, so four people work in parallel. Every stage has a fallback, so a failure never blocks the team. Hybrid search + reranker + guard are the three upgrades with the best accuracy-per-hour, and each is measured on the same question set so the results table shows what really helped.

# 11. Evaluation plan

Evaluation is the feature that makes this project stand out. The rule: no change is kept unless the numbers show it helps.

- Build the question set first (15 on Day 1, 25 on Day 2, 40 on Day 4, 80 on Day 9, 100 on Day 13). Each question has expected facts and the page that proves them.

- Run run_eval.py after every change and append a row to docs/results.md: date, change made, metrics.

- Judge answers with an LLM judge against the expected facts, and have a human check 20 of the judgments to confirm the judge is trustworthy.

- Classify every failure (Day 7 and Day 11): retrieval miss, bad chunk, generation error, or guard error. Fix the biggest category first.

- Include out-of-scope and adversarial questions (legal advice, off-topic, prompt-injection text) to test the refusal behaviour.

- Report honestly. If a target is missed, report the real number and explain why; this is more credible than a perfect-looking result.

# 12. Team roles and handoff to the leader

| Role | Owns | Main files | Hands to leader |
| --- | --- | --- | --- |
| Member 1 - Data & Documents | Collecting documents, extraction, cleaning, OCR, data sources, glossary, eval questions (with M3) | data/, scripts/download_data.py, docs/data-sources.md, docs/glossary.csv | Clean chunk files in data/processed/ and the data-sources table |
| Member 2 - Retrieval | Chunking, embeddings, vector store, BM25, fusion, reranker, query processing, speed | src/ingest/, src/retrieval/, docs/experiments.md, docs/architecture.md | A working search() that matches section 9.2 |
| Member 3 - Generation & Evaluation | Prompt, answer(), guard, output validation, evaluation harness, results and error analysis | src/generation/, eval/, docs/results.md, docs/error-analysis.md | A working answer() that matches 9.3, plus the results table |
| Leader - Integration, API, UI, Repo | Pipeline wrapper ask(), Streamlit UI, Hugging Face deployment, optional FastAPI, README, reviews and merges, issues, release tags, submission | src/pipeline.py, frontend/, src/api/, README.md, .github/ | n/a: the leader receives the main line of code from the others |

## How code reaches the leader (the main line of code)

- Every member works on their own branch: feature/<name>-<task>. Nobody commits directly to dev or main.

- When a task works, open a pull request to dev with: what changed, how to test it, and the eval numbers if relevant.

- The leader reviews within a few hours, merges to dev, and runs the eval. A PR that makes the numbers worse is sent back.

- The leader merges dev into main at the end of each phase and tags a release (v0.1, v0.2, v0.3, v1.0-rc, v1.0).

- Commit messages: feat:, fix:, docs:, data:, eval: (for example "feat: add BM25 fusion").

## Daily rhythm

- Morning standup (10 minutes): what I finished, what I do today, what blocks me.

- Evening report (one message): Done / Blocked / Next, with PR links.

- If blocked by a teammate: build against a mock that follows the contract in section 9, and keep going.

# 13. 16-day execution plan

Phases at a glance. Day 1 = Sat Oct 10 ... Day 16 = Sun Oct 25. Saturdays (Oct 10, 17, 24) are the Nepali weekend: if the team prefers, treat them as lighter catch-up days and shift unfinished tasks to the next day without moving the milestones.

| Phase | Dates | Goal | Exit criteria |
| --- | --- | --- | --- |
| 0 Kickoff | Oct 8-9 | Everyone set up; scope and contracts locked | Each member ran an embedding and an LLM call; repo ready |
| 1 Walking skeleton | Oct 10-12 (Days 1-3) | End-to-end flow with real documents | Ask a question, get a cited answer; BASELINE numbers recorded (v0.1) |
| 2 Make it good | Oct 13-16 (Days 4-7) | Hybrid search, reranker, guard, bigger eval set, first test deploy on Hugging Face Spaces (Day 5) | Measurable gains over baseline; test deploy runs; error analysis done (v0.2) |
| 3 Features and robustness | Oct 17-20 (Days 8-11) | Checklist mode, feedback, adversarial tests, stable deployment | Stable live link; 80-question eval; add-a-service guide (v0.3) |
| 4 Final improvement and freeze | Oct 21-23 (Days 12-14) | Fix top failures, final numbers, clean-machine test | Code freeze on Oct 23; v1.0-rc tagged |
| 5 Demo and submission | Oct 24-25 (Days 15-16) | Video, writeup, submission | v1.0 tagged; submission confirmed |

## Daily tasks for all 4 members

Read across a row to see what everyone does that day; read down a column to see one member's whole journey. Everything a member produces is handed to the leader as a pull request (see section 12).

| Day | Member 1 - Data & Documents | Member 2 - Retrieval (search) | Member 3 - Generation & Evaluation | Leader - Integration, API, UI, Repo |
| --- | --- | --- | --- | --- |
| PHASE 0 - Kickoff (Oct 8-9): everyone is set up, scope is locked |  |  |  |  |
| Day 0 Thu-Fri Oct 8-9 Milestone: team can run the environment | - List target documents for the 3 services (driving license, citizenship certificate, passport) with official URLs - Start downloading into data/raw/ | - Create venv; install sentence-transformers and chromadb - Smoke-test the embedding model on 5 Nepali + 5 English sentences | - Get an LLM API key; make one successful test call - Draft prompt v0 and the eval question format (section 9) | - Finish repo setup: README, LICENSE, topics, issue templates, dev + main branches - Share this document; confirm the interfaces in section 9 with the team - Fix standup time (10 min, morning and evening) |
| PHASE 1 - Walking skeleton (Days 1-3, Oct 10-12): ugly but end-to-end |  |  |  |  |
| Day 1 Sat Oct 10 Milestone: mock pipeline runs | - Collect 10 official documents total into data/raw/; log each in docs/data-sources.md - Test text extraction on every doc; rate good / ok / bad in docs/extraction-report.md | - Write src/ingest/chunk.py (300-500 tokens, 50 overlap, metadata schema) - Write src/ingest/embed_store.py to index chunks into ChromaDB | - Write src/generation/answer.py using hardcoded passages - Fix the JSON output schema; write 15 eval questions together with M1 | - src/pipeline.py: ask(query) returning mock data in the final AskResponse schema - Streamlit UI (frontend/app.py) that calls ask() and shows answer + citations - Review and merge first PRs into dev |
| Day 2 Sun Oct 11 | - Clean extracted text: Unicode NFC, remove headers/footers, fix broken Devanagari - OCR fallback (Tesseract nep+eng) for scanned docs; save to data/processed/*.jsonl | - Run ingest on all processed docs and index them - search(query, k, service) works; report hit@5 on the questions available | - eval/run_eval.py: computes hit@k, citation accuracy, answer correctness, refusal rate - Grow eval set to 25 questions (5 must be out-of-scope) | - Connect the real search() and answer() into ask() - UI: citation cards (source, page, quote) - Optional: thin FastAPI wrapper (GET /health, POST /ask) around ask() - Review and merge PRs |
| Day 3 Mon Oct 12 Milestone: v0.1 BASELINE numbers recorded | - Fill document gaps found by the eval (missing facts, bad extractions) - Re-extract the 2 worst documents | - Chunk size experiment: 300 / 500 / 800 tokens; log hit@5 for each in docs/experiments.md | - Run the full eval; record BASELINE in docs/results.md and the README table - List the top 10 failures | - Tag v0.1; open 8 "good first issue" tickets - Add repo topics and any tag Frogtoberfest requires - Read the official Frogtoberfest submission rules and note the deadline |
| PHASE 2 - Make it good (Days 4-7, Oct 13-16): retrieval, guard, evaluation, first test deploy |  |  |  |  |
| Day 4 Tue Oct 13 | - Expand eval set to 40 questions with M3 (Nepali, English, mixed) - Verify every expected answer against the source page | - Add BM25 (rank_bm25) next to dense search; fuse with Reciprocal Rank Fusion - Measure hit@5 against dense-only | - Prompt v1: forced citations, answer in the question language, structured JSON - Add output validation (retry once if JSON is invalid) | - UI: language toggle (Nepali / English), loading and error states - Review and merge PRs |
| Day 5 Wed Oct 14 Milestone: first test deploy | - scripts/download_data.py: fetch raw docs from their URLs so the repo does not redistribute files - Record licence / usage status per document | - Add reranker (bge-reranker-v2-m3): top-20 down to top-5 - Measure the gain; keep it only if it helps | - Guard v1: refuse when the best reranker score is below a threshold - Calibrate the threshold on answerable vs out-of-scope questions | - FIRST TEST DEPLOY on Hugging Face Spaces (Streamlit Space); record memory use, startup time and latency - Move secrets to Space secrets; update .env.example - README "Run locally" section, tested from scratch |
| Day 6 Thu Oct 15 | - Build a Nepali-English glossary (docs/glossary.csv) for key terms - Check Nepali expected answers for spelling and accuracy | - Query processing: detect language, expand query with glossary terms, optional service filter | - Guard v2: a second LLM check "is every claim supported by the passages?" - Block answers that fail the check | - Integrate all PRs; run the full eval - Update the README results table (mid-point) |
| Day 7 Fri Oct 16 Milestone: v0.2 checkpoint + error analysis | - Error-analysis session with the team - Fix data issues found | - Fix retrieval issues found (wrong chunk, missed chunk) | - Write docs/error-analysis.md: classify each failure as retrieval miss / bad chunk / generation / guard - Fix prompt and guard issues | - Tag v0.2 - Plan weeks 3-4 from the error analysis - Merge all fixes |
| PHASE 3 - Features and robustness (Days 8-11, Oct 17-20) |  |  |  |  |
| Day 8 Sat Oct 17 | - Stretch: add a 4th service (PAN registration or national ID) with 10 eval questions | - Make ingestion repeatable: one command rebuilds the whole index - Cache embeddings to speed up re-runs | - Checklist mode: output documents required, fees, steps, where to go - Validate it against the eval | - UI renders the checklist as tick-able items - Add copy / print button |
| Day 9 Sun Oct 18 | - Write docs/add-a-service.md and a template folder so contributors can add a service without touching code | - Profile latency per stage; target p95 under 8 s - Persistent index; lazy model loading | - Grow eval to 80 questions; LLM-as-judge script for answer correctness - Human spot-check of 20 judged answers | - Save thumbs up/down feedback to a file (function used by the UI; also in the optional API) - UI feedback buttons |
| Day 10 Mon Oct 19 | - Data QA: compare 30 random chunks to the original pages; fix OCR errors | - Handle questions that span two services; metadata filter fallbacks | - Adversarial tests: legal-advice requests, off-topic, prompt-injection text; strengthen the guard | - Error handling, request logging, basic rate limit - Review and merge |
| Day 11 Tue Oct 20 Milestone: v0.3 + stable live link | - Review every docs/ page for clarity - Add the data-source table to the README | - Write docs/architecture.md with a pipeline diagram | - Full eval run; compare against the baseline - Pick the top 3 problems for the final week | - Update the Hugging Face Space to the v0.3 build; confirm the public link works end to end - Tag v0.3 |
| PHASE 4 - Final improvement and freeze (Days 12-14, Oct 21-23) |  |  |  |  |
| Day 12 Wed Oct 21 | - Fix the top data-related failures; add missing documents | - Fix the top retrieval failures; tune k, thresholds, fusion weights | - Fix the top generation / guard failures; finalize prompt v2 | - Deployment polish; secrets via environment variables - Pre-fill sample questions in the UI for the demo |
| Day 13 Thu Oct 22 | - Final eval set of 100 questions - Final data-sources and licence table | - Freeze model settings in config.yaml; record final retrieval numbers | - Final eval run; results table + charts (matplotlib) in docs/results.md | - README final structure: problem, demo GIF, architecture, results, how to run, how to contribute |
| Day 14 Fri Oct 23 Milestone: CODE FREEZE (bug fixes only) | - Fresh-machine test: clone, follow the README exactly, report every problem | - Fix install / runtime bugs found by M1 | - Re-run the eval on the frozen build; confirm the numbers match the README | - Merge fixes; tag v1.0-rc - Confirm the deployment is live |
| PHASE 5 - Demo and submission (Days 15-16, Oct 24-25) |  |  |  |  |
| Day 15 Sat Oct 24 | - Write the short project story (problem, solution, results) - Take screenshots | - Final pass on architecture.md and CONTRIBUTING.md | - Prepare the demo script: 5 questions (2 Nepali, 2 English, 1 out-of-scope refusal) | - Record a 2-3 minute demo video - Prepare the submission text: Problem / Idea / How AI powers it |
| Day 16 Sun Oct 25 SUBMISSION DAY | - Final check of the data-sources and licence table - Answer contributors on data issues | - Smoke-test the deployed app - Answer contributors on code issues | - Final results check against the README - Answer contributors on eval issues | - Tag v1.0; submit; confirm receipt - Post all links in the team chat - Buffer for last-minute problems |

# 14. Risks and fallbacks

| Risk | Likelihood | What to do |
| --- | --- | --- |
| Nepali OCR on scanned documents is poor | High | Test on Day 1. Prefer text-based PDFs and official web pages. Treat scans as a stretch goal. Hand-correct the most important pages. |
| Embedding model is weak on Nepali | Medium | Compare bge-m3 and multilingual-e5 on the eval set; rely more on BM25 and the glossary. |
| LLM API limits or cost | Medium | Cache answers, use a cheaper model, reduce eval frequency, or switch to an open-weights model. |
| A member is blocked or absent | Medium | Mocks that follow the contracts; the leader reassigns tasks at standup. |
| Scope creep (too many services or features) | High | Stay at 3 services; the 4th service and extra features are stretch goals only. Code freeze on Day 14. |
| Document licence or redistribution unclear | Medium | Store URLs and a download script, not the files; record usage status per document. |
| Wrong answer causes real-world harm | Low but serious | Guard + citations + disclaimer on every answer; never give case-specific legal advice. |
| App runs out of memory or is too slow on the free host | High | First test deploy on Day 5 so it shows early. Use smaller models, drop the reranker if it does not help, or move to Render or a Docker VM. |
| Deployment fails late | Medium | Redeploy after every phase; keep a recorded demo video as a backup. |

# 15. Definition of done and glossary

## Final checklist (all must be true on Oct 25)

- A stranger can clone the repo, follow the README, and run the app without help (tested on a clean machine on Day 14).

- The deployed link works and the demo video is recorded.

- The results table shows baseline vs final numbers, with an honest error analysis.

- All 3 services have documents, eval questions and working answers.

- Out-of-scope questions are refused; every answered question has citations.

- LICENSE, CONTRIBUTING, issue templates, 8+ good-first-issue tickets and the add-a-service guide exist.

- docs/data-sources.md lists every document with URL and usage status.

- The submission text (Problem / Idea / How AI powers it) matches the project that was actually built.

- Frogtoberfest rules were checked and every required tag, label or form was completed.

## Glossary (plain language)

| Term | Meaning |
| --- | --- |
| RAG | Retrieval-Augmented Generation: first look up the right pages, then ask the AI to answer using only those pages |
| Chunk | A small piece of a document (a few paragraphs) stored with its source and page |
| Embedding | A list of numbers that captures the meaning of a text so similar meanings sit close together |
| Vector store | A database that finds the chunks whose embeddings are closest to the question |
| BM25 | A classic keyword search score; good at exact words and names |
| RRF | Reciprocal Rank Fusion: a simple way to merge two ranked lists into one |
| Reranker | A model that reads the question together with each candidate passage and scores how well they match |
| Hallucination | When an AI states something that is not supported by the sources |
| Guard | The check that blocks an answer when the evidence is weak |
| hit@5 | Share of questions where the correct page is among the top 5 retrieved passages |
| OCR | Optical Character Recognition: turns images of text into real text |
| PR | Pull request: a proposal to merge your branch into the shared code, which the leader reviews |

# Appendix A: Starter prompt for any AI assistant

Paste this document into the AI first, then send the message below.

You have read the Khula Gyan Project Blueprint. I am [Leader / Member 1 / Member 2 / Member 3].

Today is Day [N] of the plan (section 13). Please:

1. Summarize my tasks for today in 5 bullet points.

2. Give me the exact files to create or edit, following the repo structure (section 8).

3. Write the code, matching the interfaces in section 9 exactly, with short comments.

4. Tell me how to test it and what numbers to record.

5. Tell me what I must hand to the leader (branch name, PR description).

Rules: answers about Nepali procedures must come only from retrieved passages, never from your memory.

Keep the code simple enough for a second-year university student.

Note for the team: model names, thresholds and dates in this document are starting points. Update them in config.yaml and in this document if experiments show better choices, and tell the whole team when you do.